MOC 24 progress status:

Acres, after being bought by a new owner that has put an ‘indefinite hiatus’, and thus has dropped us as a publisher. Brandon and I have been busy and have not met to work on the book in over a year. We are currently working on Rough draft V1.5 on google drive.

For now, I want to create a timeline with benchmarks to hit by certain dates.

Work that needs to be completed:

- Change images to ones we have permission for

  - Make list of images to be changed

- Add any taxonomic changes

- Add any new fungal pathogens/endophytes/mycorrhizae interactions with cannabis

- Add bullet point summaries at end of each chapter and section

- Disease life cycle diagrams

- Cover Art

Then:

- Find 2-3 editors to review manuscript

  - Craig from Autocup-c.hartsough@gmail.com

  - Mathew Gates-content 1

  - Dr. Gauthier-content 2

  - Shouhua Wang PhD-content 3

  - Xavier Kief-xavi@divergentregeneration.com-readability 4

  - Tad Hussey? (KIS organics)-readability 1

  - Jeff Lowenfells-content readability 2

  - Brit Bunyard-Figures & readability 3

- Ask someone to write forward (Brit Bunyard?)

- Send to lab mates (Sam, Andy, Andy Hart, Beth) for review/editing

Then:

- Secure publishing partner OR self-publish

- Cover Artwork

- Manuscript format editing for ready to publish document

Timeline:

Images all changed and permission to use granted on all images- August ‘24

List of images to be changed-June ‘24

Replace or remove images-July ‘24

Chapter summaries and section summaries completed-September ‘24

3-5 Bullet point recap

All taxonomic changes complete-September ‘24

Make a list of any species changes or new species-August ‘24

Email potential editors to ask if they would be interested in editing the manuscript-mid-oct ‘24

All text complete and ready to send to editor-end of October ‘24

Book sent to 1 or more editors-November ‘24

Chapter summaries and section summaries completed-January ‘25

Finalize book images and cover art-End of December 2024

Formatting Editor-February ‘25

Book published and in print- May 2025